## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 39
PROJECT NAME | Doctor Assist for EMRI Ambulance
PROJECT MENTOR (sponsor) | Prakash Yalla, Product Lab (IIIT Hyderabad)
TEAM MEMBERS | Manan Garg
Uday Bindal
Bassam Adnan
Shivam Mittal
Mayank Mittal

## Status
PROJECT NUMBER | 39
PROJECT NAME | Doctor Assist for EMRI Ambulance
PROJECT MENTOR (sponsor) | Prakash Yalla, Product Lab (IIIT Hyderabad)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 22- January 28)
Fix meeting with client | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
GIT Repository setup | Preparation | All | 0.4 | 0.3 | Done |  | 0.1 | 33.3333
Client meeting | Coordination | All | 1 | 0.5 | Done | Basic Introduction to the Project and steps to be followed | 0.5 | 100
Research existing technology | Preparation | All | 6 | 5 | Done | Learning about Chatbots, problems faced by EMT assistants | 1 | 20
Minutes of Meeting | Documentation | Shivam, Mayank | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
Project synopsis writeup | Documentation | Manan, Uday, Bassam | 0.5 | 0.75 | Done |  | -0.25 | 33.3333
Team Meeting | Coordination | All | 1.5 | 2 | Done |  | -0.5 | 25
Status tracker | Documentation | Manan, Uday | 1 | 1.2 | Done |  | -0.2 | 16.6667
Week 2 (January 29 - February 4)
Learn ReactJS | Preparation | All | 6 | 7 | Done | Learnt it till atleast what was needed in the project | -1 | 14.2857
Learn GraphQL | Preparation | All | 5 | 7 | Done | Learnt it till atleast what was needed in the project | -2 | 28.5714
Learn NodeJS | Preparation | All | 5 | 7 | Done | Learnt it till atleast what was needed in the project | -2 | 28.5714
Client meeting | Coordination | All | 1 | 0.6 | Done | Get a better understanding of the project and discuss the design | 0.4 | 66.6667
Project concept writeup | Documentation | Manan, Uday | 1 | 1.5 | Done |  | -0.5 | 33.3333
Team Meeting | Coordination | All | 2 | 1.2 | Done | what steps to be taken | 0.8 | 66.6667
Minutes of Meeting | Documentation | Shivam | 0.5 | 0.6 | Done |  | -0.1 | 16.6667
Status tracker | Documentation | Manan | 0.75 | 0.5 | Done |  | 0.25 | 50
Week 3 (February 5 - February 11)
Team Meeting | Coordination | All | 0.5 | 0.4 | Done | Decide on any suggestions for the design | 0.1 | 25
Initiation of Implementation | Preparation | Bassam | 1 | 1 | Done | Started on the frontend | 0 | 0
Status tracker | Documentation | Manan | 0.5 | 0.5 | Done |  | 0 | 0
Week 4 (February 12 - February 18)
Client meeting | Coordination | All | 0.8 | 0.6 | Done | Told what to do on backend, final design to be presented next week | 0.2 | 33.3333
Minutes of Meeting | Documentation | Shivam, Mayank | 0.6 | 0.6 | Done |  | 0 | 0
SRS document creation | Documentation | All | 2 | 1.75 | Done |  | 0.25 | 14.2857
Team Meeting | Coordination | All | 2 | 2 | Done | Decide on backend and frontend distributions and creating the SRS doc | 0 | 0
Making Frontend and Backend | Design | All | 5 | 6 | Done |  | -1 | 16.6667
Status tracker | Documentation | Manan | 0.5 | 0.6 | Done |  | -0.1 | 16.6667
Week 5 (February 19 - February 25)
Client meeting | Coordination | All | 0.7 | 0.5 | Done | Final design given | 0.2 | 40
Started on Frontend | Development | Bassam,Uday | 5 | 6.5 | Done | Basic implementation complete | -1.5 | 23.0769
Started on Backend | Development | Bassam,Manan | 4 | 5 | Done | Basic implementation complete | -1 | 20
Test Plan Tracker | Documentation | All | 1.5 | 2 | Done |  | -0.5
Team Meeting | Coordination | All | 1.5 |  | Delayed | Delayed to after midsems
Status tracker | Documentation | Manan | 0.5 | 0.2 | Done |  | 0.3 | 150
Week 6 (February 26 - March 3)
Team Meeting | Coordination | All | 1 | 1 | Done | Disscused how to how plan further | 0 | 0
Client meeting | Coordination | All | 0.6 |  | Delayed
Status Tracker | Documentation | Manan | 0.3 | 0.3 | Done |  | 0 | 0
Week 7 (March 4 - March 10)
Client meeting | Coordination | All | 0.7 | 0.6 | Done |  | 0.1 | 16.6667
Make progress on frontend | Development | All | 10 | 11 | Done | Make good progress on the frontend and give basic backend connectivity | -1 | 9.0909
Team Meeting | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
Linking backend and frontend | Development | All | 6 | 6.5 | Done | Made a significant progress in linking the frontend and backend | -0.5 | 7.6923
Made Login Page and improved Navbar | Development | Mayank | 1 | 0.75 | Done |  | 0.25 | 33.3333
Added some database entries | Development | Manan | 1 | 1 | Done | To test the case sheet added entries | 0 | 0
Made Case Sheet | Development | Manan, Bassam | 6 | 7 | Done |  | -1 | 14.2857
Made Chat Box | Development | Uday, Bassam | 6 | 8 | Done |  | -2 | 25
Design Document | Documentation | Shivam, Mayank | 2 | 1.5 | Done |  | 0.5 | 33.3333
Status tracker | Documentation | Uday,Manan | 0.7 | 0.5 | Done |  | 0.2 | 40
Improved Sidebar | Development | Shivam, Mayank | 4 | 6 | Done |  | -2 | 33.3333
Week 7 (March 11 - March 17)
Client meeting | Coordination | All | 0.6 |  | Delayed | Due to RnD showcase client was busy
Make improvements in ChatBox | Development | Uday | 4 | 3 | Done |  | 1 | 33.3333
Integrate LLAMA Model | Development | Bassam | 3 |  | Delayed | Will be completed in R2
Improve Case Sheet | Development | Manan | 3 | 3.5 | Done |  | -0.5 | 14.2857
Status tracker | Documentation | Manan | 0.5 | 0.4 | Done |  | 0.1 | 25
Feed Database | Development | Shivam, Mayank,Manan | 3 | 2.4 | Done |  | 0.6 | 25
Team Meeting | Coordination | All | 1 | 0.7 | Done |  | 0.3 | 42.8571
Week 8 (March 18 - March 24)
Client meeting | Coordination | All | 0.6 | 0.5 | Done |  | 0.1 | 20
Team Meeting | Coordination | All | 1 | 0.75 | Done | Pre R1 meeting | 0.25 | 33.3333
R1 Presentation | Delivery | All | 0.2 | 0.2 | Done |  | 0 | 0
Status tracker | Documentation | Manan | 0.5 | 0.4 | Done |  | 0.1 | 25
Week 9 (March 25 - March 31)
Client meeting | Coordination | All | 1.5 | 1.1 | Done | To show client what is build till now and what in future, discuss about the LLM | 0.4 | 36.3636
Team Meeting | Coordination | All | 0.5 | 0.5 | Done | Discuss work distribution for R2 | 0 | 0
Worked on signup page | Development | Shivam, Mayank | 3 | 2.4 | Done |  | 0.6 | 25
Improve Case Sheet | Development | Manan | 2 | 2 | Done |  | 0 | 0
Making CSS and backend changes | Development | All | 1.5 | 1 | Done |  | 0.5 | 50
Link open page to main page | Development | Bassam | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Manan | 0.5 | 0.4 | Done |  | 0.1 | 25
Week 10 (April 1 - April 7)
Team Meeting | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
Meeting Scheduled | Coordination | All | 0.1 | 0.1 | Done |  | 0 | 0
TA meet | Coordination | All | 0.4 | 0.5 | Done | Showed our code till now | -0.1 | 20
CSS changes | Design | All | 1.5 | 2 | Done |  | -0.5 | 25
Status tracker | Documentation | Manan, Uday | 0.5 | 0.4 | Done |  | 0.1 | 25
Week 11 (April 8 - April 14)
Team Meeting | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
Client meeting | Coordination | All | 0.6 | 0.3 | Done |  | 0.3 | 100
Implemented admin page | Development | Shivam, Mayank | 5 | 5.5 | Done |  | -0.5 | 9.0909
Upload documents | Development | Shivam, Mayank, Manan | 7 | 8 | Done |  | -1 | 12.5
Implementing API calls to LAMA | Development | Manan | 6 | 5 | Done | API calls provided were ambiguous and the client is looking into it | 1 | 20
CSS changes to vital sheet | Development | Manan | 2.5 | 2 | Done |  | 0.5 | 25
Status Tracker | Documentation | Manan | 0.5 | 0.5 | Done |  | 0 | 0
Week 11 (April 15 - April 20)
Team Meeting | Coordination | All | 2 | 1.5 | Done | Implement and integrate final modules | 0.5 | 33.3333
Client meeting | Coordination | All | 1 | 0.4 | Done |  | 0.6 | 150
Connect LAMA model for querying | Development | Manan | 7 | 5 | Done |  | 2 | 40
Final changes to CSS | Development | All | 5 | 4 | Ongoing |  | 1 | 25
Changes to admin page | Development | Shivam, Mayank, Manan | 7 | 5 | Ongoing |  | 2 | 40
Make changes to chat page css | Development | Uday | 3 | 2.5 | Ongoing |  | 0.5 | 20
Fix bugs | Development | All | 4 | 2.5 | Ongoing |  | 1.5 | 60
Test Tracker V3 | Documentation | Uday | 1 | 0.75 | Done |  | 0.25 | 33.3333
Status tracker | Documentation | Manan | 0.6 | 0.6 | Done |  | 0 | 0
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically